DIGITAL WORKPLACE TRANSFORMATION PORTFOLIO # Hardware Refresh — Four Playbooks A 360-device, four-site endpoint program from standards and procurement through user acceptance, secure retirement, service transition, and benefits. Kanban · Scrum · Predictive / Waterfall — PMBOK 8 aligned · Hybrid 360 devices; 4 sites; 18 weeks; $792K modeled authorization. PORTFOLIO GUIDE · AUGUST 2026

# How to read this portfolio

Truth boundary Company ABC is fictional. All case dates, quantities, costs and results are scenario assumptions. Verified endpoint, digital-workplace and delivery-method experience is separated from modeled results. Product and standards references are current primary-source guidance as of August 25, 2026.

Table 1. Experience-informed design

| Verified experience | Control informed | Not claimed |
| --- | --- | --- |
| 37K Macs / 300K Windows modern management | Inventory, build, compliance, telemetry, support | The 360-device result is fictional |
| Intune, SCCM/MECM, Jamf, ServiceNow, Tanium, BeyondTrust | Provisioning, management, workflow, support, analytics | Actual Company ABC licensing/architecture is unknown |
| 98% OS compliance; endpoint standards; audit partnership | Release thresholds, policy, evidence, sanitization | No certification or legal opinion |
| Scrum/Kanban/program leadership | Four tailored delivery systems | Method metrics are modeled |

Reusable template fields device/site/persona baseline · method rationale · standards · budget/schedule · success measures · service/benefit owners

# Program architecture and outcomes

Table 2. Scenario scope

| Dimension | Filled example | Acceptance |
| --- | --- | --- |
| Devices | 270 laptops; 60 desktops; 30 phones | 360 final dispositions |
| Sites | Three offices plus remote/all-site cohort | Manager roster, blackout and readiness sign-off |
| Technology | Intune/Entra target; SCCM/MECM approved existing-device path | Versioned build, join/enrollment, security and support |
| User/data | 76 apps; KFM/approved backup; specialized personas | Task-based app/data/accessibility acceptance |
| Old assets | Return, custody, hold release, sanitization and disposition | No unknown serial or evidence gap |
| Financial | $792K baseline; $748.4K forecast | Planning assumption; reconcile PO/invoice/credits/reserve |

Table 3. Illustrative checkpoint

| Measure | Result | Interpretation |
| --- | --- | --- |
| Deployed | 344 / 360 | 16 controlled exceptions remain |
| First-time-right | 336 / 344 = 97.7% | Meets 97% target |
| Data validation | 342 / 344 = 99.4% | Two owned exceptions |
| Compliant within 24h | 339 / 344 = 98.5% | Five remediations |
| Old devices returned | 334 / 344 = 97.1% | Remote return action open |

# Method selection

Table 4. Four operating systems

| Method | Best fit | Primary controls | Watch-out |
| --- | --- | --- | --- |
| Kanban | Variable ready demand and exceptions | Workflow, WIP, SLEs, age, cycle time, throughput | A board without pull/limits is only visualization |
| Scrum | Cross-functional team can deliver accepted wave Increments | Product Goal, Backlog, Sprints, DoD, Review/Retro | Do not count staged devices as Done |
| Predictive | Fixed quantities, site order, procurement and formal approvals | WBS, IMS, baselines, gates, change, EVM | Unknowns need rolling-wave detail, not false precision |
| Hybrid | Fixed compliance/supply guardrails plus variable user/app work | Baseline/gates + pull/WIP + rolling waves | One source of truth per control; no competing plans |

Recommendation Hybrid is the modeled recommendation because supply, budget, security and site commitments are fixed, while application defects, user readiness, local data, appointments and remote returns vary. The other three playbooks remain complete for comparison.

# Kanban playbook

Table 5. Definition of Workflow

| State | Exit policy | WIP |
| --- | --- | --- |
| Ready | Roster/persona, hardware, app/data precheck and appointment feasible | 60 |
| Staging | Build/security/asset test passes | 24 |
| Scheduled | User/site communication and kit ready | 40 |
| Deploying | Task/data/user acceptance | 12 |
| Hypercare | T+5 measures pass or exception assigned | 30 |
| Return/Sanitize | Disposition evidence accepted | 35 |

Service classes: Expedite, Fixed Date, Standard and Intangible; one Expedite maximum.

Review aging at 50% of SLE, swarm at 75%, escalate or reshape at 100%.

Latest modeled flow: 42 devices/week, median 3.4 days, P85 6.2 days; stop starting and finish exception/return work.

Done includes new-device acceptance and old-asset reconciliation; handoff alone is not the delivery point.

Reusable template fields workflow states · entry/exit · WIP · classes · SLEs · cadences · flow/outcome metrics · policy experiments

# Scrum playbook

Product Goal: by Sprint 9, all 360 assignments have an accepted secure replacement or approved final exception; old assets are reconciled; Service Operations owns the stable service.

Table 6. Scrum design

| Element | Filled example | Evidence |
| --- | --- | --- |
| Accountabilities | Endpoint Service Owner; Agile Delivery Lead; cross-functional Developers | Clear Product Owner/Scrum Master/Developers |
| Sprints | Nine two-week Sprints | Sprint Goal, Sprint Backlog and usable Increment |
| Increment | Accepted cohort plus security/data/asset/support evidence | Strict Definition of Done |
| Progress | 344 accepted; 16 PBIs remain | Incomplete work returns to Product Backlog |
| Inspection | Stakeholder Review; Retrospective improvement | Task evidence and one measurable experiment |

Reusable template fields Product Goal · accountabilities · Sprint events · Product Backlog · Sprint Goal · Definition of Done · release/wave gates · outcome metrics

# Predictive / Waterfall playbook

PMBOK Guide Eighth Edition remains approach-neutral. This version uses a predictive sequence because quantities, sites, budget, supply, standards and approvals can be baselined; exceptions receive rolling-wave detail inside controlled work packages.

Table 7. Predictive controls

| Control | Filled example | Decision use |
| --- | --- | --- |
| WBS | Governance; supply; engineering; deployment; retirement; reserve | Accepted work packages/control accounts |
| IMS | Week 1–18 with pilot and four waves | Critical path and milestone forecast |
| Gates | Charter, baseline, build/pilot, scale, wave, retirement, close | Formal authorization |
| EVM | SPI 0.97; CPI 1.03; EAC $748.4K | Schedule/cost forecast with acceptance-based earning |
| Change | $15K/five-day PM/CCB threshold; steering above | Protect baselines and controls |

Reusable template fields PMBOK 8 mapping · WBS · IMS · cost baseline/EVM · stage gates · quality · change thresholds · closure/benefits

# Hybrid playbook

Table 8. Integrated operating model

| Layer | Predictive guardrail | Adaptive control |
| --- | --- | --- |
| Program | 360 scope, $792K, Week 18, standards | Reprioritize cohorts inside thresholds |
| Supply/build | PO, receipt, build release and pilot gates | Daily pull; staging WIP 24; defect learning |
| Deployment | Four site milestones; T-5/T-1 go/no-go | Two-week horizon; readiness/capacity pull |
| Exceptions | Risk/change authority; full disposition | Dedicated lane, WIP 10, aging and swarming |
| Reporting | Baseline/forecast, quality, budget, RAID | Flow/outcome metrics and retrospectives |

One source of truth per control: baseline for authorized scope/cost/date; wave register for released quantities and acceptance; board for current state; inventory for serial identity; RAID for exposure. Dashboards derive from those sources rather than narrative reconciliation.

Reusable template fields guardrails · adaptive work · planning horizons · workflow/WIP · wave gates · decision matrix · reconciliation · metrics

# Shared technical control pack

Table 9. Technical and operational controls

| Control | Required evidence | Stop condition |
| --- | --- | --- |
| Device build | Version, join/enrollment, apps, update, drivers, support | Unknown/mismatched build or critical app |
| Security | Encryption, EDR, firewall, supported OS, compliance, least privilege | Missing protection or unapproved exception |
| Applications | 76 dispositions; Tier 0/1 package/license/task test/fallback | Critical workflow failure |
| User data | Precheck, sync/backup, counts/samples, task/user acceptance | Unknown local data, sync error or hold |
| Asset | New/old serial, user/site/wave, custody scans, authoritative state | Unknown serial, loss or tamper |
| Sanitization | Approved method/program, validation, certificate, final disposition | Hold not released or evidence/validation failure |
| Support | Queue, knowledge, staffing, spares, escalation, vendors, monitoring | Cannot restore affected users |

# Wave and user journey

Table 10. Deployment waves

| Wave | Planned | Deployed | FTR | Data | 24h compliance | Returns | Exceptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pilot | 20 | 20 | 19 | 20 | 20 | 20 | 0 |
| Site A | 95 | 94 | 92 | 94 | 93 | 92 | 1 |
| Site B | 90 | 87 | 85 | 86 | 86 | 84 | 3 |
| Site C | 75 | 71 | 69 | 71 | 70 | 68 | 4 |
| Remote/all | 80 | 72 | 71 | 71 | 70 | 70 | 8 |
| Total | 360 | 344 | 336 | 342 | 339 | 334 | 16 |

T-30 managers validate roster, blackout, persona and local needs; T-14 users receive appointment/preparation/data/app/accessibility instructions.

T-5 prechecks classify Ready, controlled exception with new date, or not authorized; T-1 go/no-go verifies security, data, app, logistics, support and rollback.

Day 0 verifies identity, old-asset custody, new-device issue, user tasks and acceptance; T+1/T+5 measures compliance, tickets, data, returns, satisfaction and lessons.

Denominator rule A reschedule, leave, accessibility dependency, application defect or logistics delay remains in the 360-device denominator until it reaches an approved final disposition.

# Secure retirement and chain of custody

NIST SP 800-88 Rev. 2 is applied as enterprise sanitization-program guidance: classify data/media, select an organization-approved method/standard, authorize tools/vendors, preserve custody, validate effectiveness, retain evidence and manage reuse/disposal. The project does not invent a destructive technique.

Table 11. Custody states

| State | Evidence | Gate |
| --- | --- | --- |
| User handoff | Old asset ID/serial, person, time, location, condition | Identity and data release |
| Secure storage | Cage/container/seal and scan | No unknown state |
| Transport/processor | Pickup, tracking, receipt and exception | Vendor/chain acceptance |
| Sanitization | Method/tool/version, result, validator, exception | Approved program and hold release |
| Final disposition | Certificate/reference and reuse/recycle/destruction | Asset/records/security acceptance |

Quarantine rule Unknown identity or serial, missing hold release, suspected loss/tamper, failed sanitization validation or vendor evidence gap is quarantined and escalated. An invoice alone never closes custody.

# Governance, RAID, and financial control

Table 12. Top RAID items

| ID | Exposure | Score | Response |
| --- | --- | --- | --- |
| HW-R-003 | Critical app/driver/VPN/peripheral failure | 16 | Persona pilot, versioned package, fallback, owner acceptance |
| HW-R-002 | Local/application data not protected | 15 | Precheck, KFM/backup, validation, sanitize hold |
| HW-I-005 | 16 application/accessibility/leave/logistics exceptions | 15 | Named owner/date/workaround and specialized capacity |
| HW-R-004 | Custody/sanitization evidence gap | 10 | Serial scans, secure storage, validation and quarantine |

Table 13. Budget

| Measure | Modeled value | Rule |
| --- | --- | --- |
| Baseline | $792K | Devices, accessories, shipping, staging, support, sanitization, change, reserve |
| Forecast | $748.4K | Update from PO, receipt, invoice, labor, tax, credit and ETC |
| Variance | $43.6K favorable | Do not trade quality/acceptance for cost |
| Benefits | Not yet realized | Operational owner + Finance validate source evidence |

# Service transition, closure, and benefits

Exit wave hypercare after five stable business days, no Sev 1, first-time-right at least 97%, compliance at least 98% within 24 hours, and open defects inside the agreed service objective.

Service Operations accepts build, CMDB/inventory, knowledge, queue, monitoring, spares, vendor, escalation, on-call, KPIs and known risks.

Close only when 360 of 360 new/old asset dispositions reconcile; data/holds and sanitization evidence close; POs/invoices/credits/warranties reconcile; risks/issues transfer; sponsor accepts outcome.

Benefits continue after closure: supported-device rate, compliance, startup/app reliability, ticket/contact rate, satisfaction, repair/warranty and validated avoided cash cost.

Reusable template fields hypercare exit · service acceptance · asset reconciliation · financial/vendor closure · open-item transfer · lessons/actions · benefit owners/measures

# Artifact inventory and research

Table 14. Repository package

| Package | Method-specific artifacts | Shared evidence |
| --- | --- | --- |
| Kanban | Workflow/policies, board, flow metrics, service review, status | Full endpoint/data/asset control pack |
| Scrum | Product Goal/Backlog, Sprint plan, DoD, metrics, status | Full endpoint/data/asset control pack |
| Predictive | PMBOK 8 map, WBS, IMS, gates/change, quality, EVM, status | Full endpoint/data/asset control pack |
| Hybrid | Integrated governance, rolling-wave/flow, plan, metrics, status | Full endpoint/data/asset control pack |
| Workbook | Four dashboards with formulas/charts | RAID, inventory, waves, budget, custody, sources, templates |

Primary-source research includes PMI PMBOK Guide Eighth Edition, PMI Process Groups and Agile Practice Guides, the Scrum Guide, the Kanban Guide, NIST SP 800-88 Rev. 2, Microsoft Windows Autopilot, Intune compliance, OneDrive Known Folder Move and Endpoint Analytics guidance.