ENTERPRISE TRANSFORMATION PORTFOLIO # M&A IT Integration Playbooks A complete, anonymized program from clean-team discovery and Day 1 through secure convergence, decommissioning, and benefits ownership. Agile · Predictive / Waterfall — PMBOK Guide Eighth Edition aligned 680 workers; 745 endpoints; 142 applications; $1.86M modeled authorization. PORTFOLIO GUIDE · AUGUST 2026

# How to read this portfolio

Truth boundary Company ABC and Company XYZ are fictional. All project dates, quantities, costs, performance, and decisions are scenario assumptions. Verified experience is separated from case results; product and standards references are current primary-source guidance as of August 25, 2026.

Table 1. Evidence classes

| Class | Meaning | Example |
| --- | --- | --- |
| Verified experience | Supported by supplied resume/profile | Nine M&A endpoint integrations |
| Public source | Authoritative current guidance | PMI PMBOK 8; NIST CSF 2.0 |
| Scenario assumption | Fictional planning input | 680 workers; $1.86M |
| Derived calculation | Arithmetic from disclosed inputs | 665 / 680 = 97.8% |
| Unknown | Requires discovery, approval, test, contract, or source record | Mailbox volume; legal-hold population |

The website contains the full artifact library and filterable workbook. This guide is the executive field manual: it shows the control architecture, method differences, key registers, and decision rules.

Reusable template fields deal thesis · close date · clean-team rules · headcount/sites/devices/apps · target state · success measures · method rationale

# Scenario and outcome architecture

Table 2. Scenario at a glance

| Dimension | Filled example | Acceptance truth |
| --- | --- | --- |
| Day 1 | 680 workers across three offices and remote | 665 fully ready; 15 owned exceptions |
| Identity/endpoints | Company ABC target; temporary bridge; 745 endpoints | Unique identity, MFA, device path, least privilege, logs |
| Network | Three sites, two clouds, four subnet collisions | No unresolved overlap; restricted, redundant, observable flows |
| Collaboration | Google Workspace, Slack, Asana, Jira | Counts, samples, permissions, holds, integrations, business acceptance |
| Applications | 142 discovered; 37 overlaps; 22 targeted | Owner, criticality, disposition, dependency, contract and evidence |
| Financial | $1.860M baseline; $1.782M forecast | Planning assumption; Finance validates actual/realized value |

## Experience that informs the design

Nine enterprise M&A endpoint integrations covering standards, access, onboarding, tooling, support, and continuity.

Digital-workplace leadership across 37,000 Macs and 300,000 Windows endpoints with modern management and telemetry.

Collaboration-platform work spanning Google Workspace, Slack, Box, Microsoft 365, Teams, OneDrive, Jira, and Confluence.

A 45-person portfolio, $14 million financial responsibility, vendor savings, security/audit partnership, endpoint standards, and cross-functional delivery.

What this does not claim The modeled Company ABC/XYZ project, quantities, dates, costs, migration results, and closeout are not presented as a prior employer engagement.

# Agile playbook

Product Goal: acquired workers perform priority work securely on Day 1, then Company ABC progressively converges technology and removes temporary risk and cost with measured acceptance.

Table 3. Agile operating model

| Control | Filled example | Evidence |
| --- | --- | --- |
| Cadence | Ten two-week Sprints; reviews, retrospectives, twice-weekly dependencies | Sprint goal, accepted Increment, decision log |
| Releases | Foundation; Day 1; migration waves; convergence/closure | Release outcome and shared gate |
| Backlog | Outcome, owner, priority, acceptance, risk, dependency, evidence | One ordered integration backlog |
| Quality | Definition of Ready/Done includes security, data, business, operations | No tool-success-only completion |
| Metrics | Outcome burn-up, cycle time, throughput, defects, blockers, budget | Three Sprints: 176/186 forecast points; P85 6.9 days |

## Agile gate tension

Legal close, Day 1, security/privacy approval, contract dates, and destructive decommission actions are fixed constraints. Discovery and solution work are adaptive. The backlog may reorder work; it may not delete control evidence to protect velocity.

Reusable template fields Product Goal · value streams · Sprint length/events · release map · backlog schema · DoR/DoD · metrics · fixed constraints

# Predictive / Waterfall playbook

PMBOK Guide Eighth Edition is delivery-approach neutral. This playbook is called Predictive / Waterfall because it uses formal scope, WBS, schedule and cost baselines, sequenced stage gates, integrated change control, quality assurance, and earned value reporting.

Table 4. PMBOK 8 application

| Element | Portfolio application | Primary evidence |
| --- | --- | --- |
| Six principles | Holistic view, value, embedded quality, accountability, sustainability, empowered teams | Charter, acceptance, governance, closure |
| Seven domains | Governance, scope, schedule, finance, stakeholders, resources, risk | Baselines, owners, measures and registers |
| Process groups | Initiating, Planning, Executing, Monitoring/Controlling, Closing | Lifecycle and gate sequence |
| Tailoring | Formal legal/security/data/decommission gates; rolling-wave detail for unknowns | Tailoring statement and change thresholds |

Table 5. Predictive performance checkpoint

| Measure | Evidence | Interpretation |
| --- | --- | --- |
| SPI | 0.97 at Week 12 | Schedule watch; Week 24 unchanged |
| CPI | 1.02 | Cost favorable; never substitutes for acceptance |
| EAC / VAC | $1.782M / $78K favorable | Fictional; update from source financial records |
| Critical control | Jira production cohort held | Quality gate prevents premature release |

Reusable template fields tailoring · WBS/control accounts · IMS/critical path · cost baseline/EVM · stage gates · quality · change thresholds · closure

# Shared control pack

Table 6. Shared artifacts and accountable questions

| Artifact | Question it answers | Completion evidence |
| --- | --- | --- |
| Charter/governance | What is authorized; who decides? | Signed outcomes, limits, forums, thresholds |
| Day 1 plan | Can every worker perform priority work? | Roster/persona/device/access/support evidence |
| Identity/access | Is the identity bridge controlled and temporary? | Unique IDs, least privilege, privileged review, expiry |
| Network/infrastructure | Can required traffic flow safely and observably? | Collision, DNS, route, rule, failover and log tests |
| Collaboration migration | Is content usable, permitted, retained and integrated? | Counts, samples, permissions, holds, bots/webhooks |
| Application rationalization | Does every app have a safe target disposition? | 142/142 owner, decision, dependency and exit evidence |
| Security/privacy | Are risk, data and legal controls embedded? | NIST CSF outcomes, data approvals, risk acceptance |
| Cutover/hypercare | Can we stop, recover and hand off? | Time-stamped runbook, triggers, rollback and service acceptance |

# Day 1 readiness and support

Table 7. Modeled Day 1 readiness

| Cohort | Population | Fully ready | Exceptions | Control |
| --- | --- | --- | --- | --- |
| HQ Site A | 280 | 272 | 8 | Loaners + temporary approved access |
| Office Site B | 190 | 186 | 4 | Site runner + spares |
| Office Site C | 110 | 107 | 3 | Concierge appointments |
| Remote | 100 | 100 | 0 | Courier + virtual support |
| Total | 680 | 665 (97.8%) | 15 | Every exception has owner/workaround/expiry |

Freeze and reconcile HR roster at T-10, T-3 and T-0; resolve duplicates, contractors, managers, personas, sites, devices and special access.

Provision destination identities disabled; validate MFA, privileged roles, service identities, licenses and recovery before release.

Stage devices and instructions by site/remote logistics; test standard, executive/delegate, developer/admin, shared, contractor and accessibility personas.

Open a staffed command center; measure login, compliance, collaboration, priority app, incident, workaround and user-impact evidence at T+2/T+8.

Stop rule Hold a cohort if roster-to-identity mismatch exceeds 1%, a privileged path is unapproved, a Tier 0 workflow fails, or support cannot receive and route cases. Preserve the approved source path; rollback is not deletion.

# Migration workstreams and acceptance

Table 8. Platform migration control

| Platform | Scope | High-risk edge cases | Acceptance |
| --- | --- | --- | --- |
| Google Workspace | 610 users; Gmail, Calendar, Drive, Shared Drives, Groups | Delegates, sharing, ownership, holds, links, unsupported items | 99.5%+ counts plus samples, permissions and business tests |
| Slack | 520 users; 286 channels | Private/shared channels, guests, history, files, apps, bots, webhooks | Membership/history/integrations/retention accepted |
| Asana | 280 users | Owners, dates, custom fields, archives and privacy | Project/task/field reconciliation |
| Jira | 190 users | Email identity, groups, permissions, apps, filters, boards, automation | User/group-first mapping and workflow regression |
| Applications | 142 discovered | Shadow IT, contracts, data, APIs, ownerless apps | Owner, disposition, migration/archive, contract and decommission evidence |

A migration batch is not accepted on a tool-success message. The accountable owner reviews object counts, defined exclusions, representative samples, permissions, retention/legal hold, critical integrations, searchability and business workflows. The source remains available/read-only for the approved retention window.

# Governance, risk, and financial control

Table 9. Top RAID items

| ID | Exposure | Score | Response |
| --- | --- | --- | --- |
| MA-R-001 | Identity duplicates/stale contractors | 20 | T-10/T-3/T-0 reconciliation and exception path |
| MA-R-002 | Subnet overlap disrupts routing/DNS | 15 | NAT/renumber, isolated test, route withdrawal |
| MA-R-003 | Collaboration permissions/retention/integrations differ | 15 | Identity-first mapping, legal review, pilot and validation |
| MA-I-004 | 15 Day 1 worker exceptions | 15 | Workarounds, owners, expiry and daily burn-down |

Table 10. Budget control

| Measure | Modeled value | Control |
| --- | --- | --- |
| Authorized baseline | $1.860M | Scenario assumption |
| Forecast at completion | $1.782M | Weekly ETC/EAC from work packages |
| Forecast variance | $78K favorable | Protect reserve and quality gates |
| Savings | Not booked | Finance validates contract/invoice stop; capacity is not cash |

# Cutover, rollback, and hypercare

Table 11. Gate and command path

| Checkpoint | Required evidence | Decision |
| --- | --- | --- |
| T-10 | Roster, inventory, design, vendor, communications, test status | Continue / recover / de-scope |
| T-3 | No Sev 1; Tier 0 tests; rollback; staffing | Go / conditional go / hold |
| T-0 | Backups/exports, freeze, monitoring, bridge, approvals | Start cutover |
| Batch validation | Counts, samples, permissions, workflow, support | Accept / retry / rollback cohort |
| Hypercare exit | Stable SLA, defects, knowledge, on-call, owner acceptance | Transfer to operations |

Rollback is assessed per identity cohort, route/rule group, application, site and data batch—not as one all-or-nothing command.

Triggers include security control failure, permission variance, reconciliation below 99.5%, identity failure above 2%, Tier 0 workflow failure, or inability to restore within the approved objective.

Exit hypercare after five stable business days, no Sev 1, accepted service ownership, controlled aged defects and documented residual risk.

# Executive dashboard and decision rules

Table 12. Illustrative checkpoint

| Dimension | Evidence | Decision |
| --- | --- | --- |
| Day 1 | 665/680 fully ready; 674/680 authentication | Close 15 exceptions by Day 3 |
| Migration | Workspace pilot 99.7%; Slack/Jira integration defects open | Hold affected production scope |
| Applications | 142 discovered; five Tier 2 owners unresolved | Assign/restrict before integration |
| Schedule | Agile Week 20 or Predictive Week 24 forecast | Method-specific forecast; same acceptance |
| Finance | $1.782M forecast | Favorable but low-confidence scenario value |

Management rule A dashboard is green only when its source register is current. Unknown denominator, unowned exception, missing approval, untested rollback or unvalidated destructive action is visible and blocks the affected decision.

# Artifact inventory and research

Table 13. Repository package

| Package | Examples | Format |
| --- | --- | --- |
| Shared controls | Charter; governance; Day 1; IAM; network; collaboration; apps; security; change; cutover; vendor | Rendered web pages + Markdown |
| Registers | RAID; dependencies; RACI; app portfolio; readiness; validation; budget; sources | Rendered tables + CSV |
| Agile | Playbook; roadmap; backlog; Sprint plan; DoR/DoD; metrics; status | Web/Markdown/CSV |
| Predictive | Playbook; PMBOK 8 map; WBS; IMS; gates/change; quality; EVM; status | Web/Markdown/CSV |
| Control workbook | Two dashboards and reusable source registers/formulas | XLSX |

Primary-source research includes PMI PMBOK Guide Eighth Edition, PMI Process Groups and Agile Practice Guides, the 2026 PMP exam update, NIST CSF 2.0, Microsoft Entra multi-tenant and Azure VPN guidance, Google Workspace migration resources, Slack migration documentation, Atlassian migration guidance, and Asana import/export documentation.

Reusable template fields source title · publisher · URL · access date · portfolio use · authority · validation owner